## Summary
BOOKDOC2026 - API & Operational Readiness
Contract names are proposed planning inputs. No endpoint or package implementation is authorized by this workbook.
Area | Confirmed direction | Next gate | Status
Tenancy | Independent clinic tenant; platform control plane | Isolation reference slice | Confirmed
Backend jobs | API managed; separate production Worker | Retry/dead-letter/idempotency tests | Confirmed
Reporting | Admin management; permission-filtered Portal | Active-report classification | Confirmed
Printing | Browser/PDF first; constrained agent later | Pilot printer evidence | Deferred
Mobile | Patient M1 then evidence-selected staff stages | Stable API contracts | Proposed
Operations | 10 tenants year 1; 50 year 3 | Peak concurrency and volume model | TBD

## API_Catalog
Proposed API and Permission Catalog
All endpoints are versioned, tenant-scoped and return standardized errors. Exact routes require ADR/API review.
Area | Method | Proposed route | Permission | Scope | Idempotency/concurrency | Consumer | Status
Clinic application | POST | /api/v1/clinic-applications | Public verified submit | Own application | Submission key | Applicant | Proposed
Clinic application | POST | /api/v1/platform/clinic-applications | Tenants.Register | Control plane | Operation key | Platform Admin | Proposed
Clinic approval | POST | /api/v1/platform/clinic-applications/{id}/approve | Tenants.Approve | Control plane | Version required | Platform Admin | Proposed
Document types | POST | /api/v1/platform/onboarding-document-types | OnboardingDocumentTypes.Manage | Control plane | Code/version unique | Platform Admin | Proposed
Branch configuration | PUT | /api/v1/branches/{branchId}/configuration | Branches.Configuration.Manage | Authorized tenant/branch | Base version / ETag | Admin | Proposed
Communication verification | POST | /api/v1/integrations/communication-identities/{id}/verification-events | Providers.VerificationCallback | Resolved tenant/branch + identity | Provider event ID | Provider/Worker | Proposed
Patients | GET | /api/v1/patients | Patients.View | Tenant/branch + masking | ETag for detail | Admin/Portal/MAUI | Proposed
Patients | POST | /api/v1/patients | Patients.Create | Tenant/branch | Idempotency key | Portal | Proposed
Slots | GET | /api/v1/availability | Appointments.View | Tenant/branch/resources | Versioned projection | Portal/MAUI | Proposed
Booking | POST | /api/v1/bookings | Appointments.Book | Tenant/branch/resources | Required idempotency + transaction | Portal/MAUI | Proposed
Queue | POST | /api/v1/queue-tickets/{id}/call | Queues.Call | Branch/service point | Row version | Portal | Proposed
Encounter | POST | /api/v1/encounters/{id}/sign | Encounters.Sign | Care relationship | Version/hash | Portal/MAUI later | Proposed
Reports | POST | /api/v1/report-executions | Reports.Run | Host + report + data scope | Execution idempotency | Admin/Portal | Proposed
Report schedules | POST | /api/v1/report-schedules | Reports.Schedule | Admin + approved scope | Version required | Admin | Proposed
Print jobs | POST | /api/v1/print-jobs | Printing.Submit | Tenant/branch/printer | Required idempotency | Admin/Portal | Deferred

## Integration_Register
Integration and Vendor Register
Vendor names, commercial terms and production credentials remain TBD. Provider adapters must minimize shared patient data.
Integration | Release | Purpose | Required decision/evidence | Failure/reconciliation | Data/privacy | Owner | Status
Email | MVP | Transactional and secure report links | Provider/domain/bounce webhook | Retry/dead letter/complaint | No sensitive attachment by default | Platform | TBD
WhatsApp Business | MVP | Approved templates/notifications | BSP/opt-in/template/sender approval | Webhook/idempotency/status | Minimum variables | Platform | TBD
SMS/DLT | Conditional | Fallback/approved notices | Entity/header/template/provider | Delivery receipt/retry | Minimum content | Platform | TBD
FCM/APNs | MAUI M1 | Push and deep links | Project ownership/token lifecycle | Invalid token removal | Opaque event/generic text | Mobile | TBD
SignalR | MVP | Status invalidations | Scale/backplane/group policy | Reconnect/API refresh | No clinical payload | Platform | Proposed
Payment gateway | Later approved | Online payment/refund | Provider/webhook/settlement | Idempotent reconciliation | Financial minimum | Finance | TBD
ABDM/ABHA | Separate increment | Health record interoperability | Role/sandbox/certification | Consent/downtime | ABDM policy | Clinical/Platform | Deferred
PACS/RIS/LIS | Future/pilot decision | Imaging/lab exchange | Protocol/vendor sandbox | Patient/order/result match | Clinical sensitive | Clinical | Deferred
Object storage/scan | MVP | Documents and snapshots | India region/key/scan SLA | Quarantine/retry/restore | Encrypted/signed access | Platform | TBD
Local print agent | R5 | Receipt/slip/label | Printer/media/workstation | Offline/duplicate/wrong branch | Short-lived payload | Operations | Deferred

## Environment_Readiness
Environment and Operational Readiness
Production data and credentials never seed lower environments.
Control | Development | Integration | Staging | Production | Evidence/owner | Status
Tenant/data isolation | Synthetic | Multi-tenant tests | Prod-like scopes | Mandatory | Security owner | Proposed
Worker topology | API-hosted or separate | Separate mode tests | Separate process | Separate process(es) | Platform owner | Confirmed
Secrets/keys | Dev secret store | Environment-specific | Environment-specific | Managed and rotated | Security owner | Proposed
Database migrations | Clean/upgrade tests | Automated | Prod-like rehearsal | Reviewed rollout | Data owner | Proposed
Backups | Optional | Test fixtures | Restore rehearsal | PITR + scheduled restore test | Operations | TBD
Monitoring | Developer telemetry | Integration traces | Alert rehearsal | Tenant-safe SLO/alerts | Operations | TBD
Vendor endpoints | Sandbox/stub | Sandbox | Sandbox/prod-like | Production | Integration owner | TBD
Patient data | Synthetic only | Synthetic only | Synthetic/anonymized approved | Live restricted | Privacy owner | Confirmed
Release evidence | Build/test | Contract/migration | Full candidate | Go/no-go record | Delivery owner | Proposed
Disaster recovery | N/A | Component test | Exercise | Approved RPO/RTO exercise | Operations | TBD

## Implementation_Gates
Implementation Readiness Gates
A module is not Ready while a blocking safety, tenancy, legal, owner or source-data field is TBD.
Gate | Required evidence | Owner | Dependency | Current result | Blocker / next action | Status
G0 Discovery | Live schema + anonymized sample + secret rotation | Discovery/Data | Source access | Not met | Obtain live evidence | Blocked
PD Product | Scope, tenant model, roles, scale | Product | Owner approval | Mostly met | Approve remaining questionnaire | Proposed
SEC Security | Threat model + tenant isolation + privacy map | Security/Privacy | Delhi/legal review | Not met | Name reviewers | TBD
UX Experience | Sitemap + core flows + accessibility states | UX/Product | Workflow workshops | Not met | Create low-fidelity flows | TBD
PHY Specialty | Approved measures/templates + 10 cases | Clinical | Physiotherapy representatives | Not met | Run workshop | TBD
ORT Specialty | Approved exam/procedure/referral + 10 cases | Clinical | Orthopaedic representatives | Not met | Run workshop | TBD
API Contract | Errors/idempotency/authorization conventions | Architecture | Reference slice design | Not met | Create ADR/contracts | TBD
DATA Database | Profile + ownership + migration/index review | Data owners | G0 | Not met | Profile database | Blocked
WRK Worker | Task inventory + handler/retry/dead-letter design | Platform | Legacy task discovery | Not met | Inventory service tasks | TBD
REP Reports | 45+43 catalog + owners + goldens | Reporting | Legacy users/data | Not met | Run RP0 classification | TBD
OPS Operations | RPO/RTO + capacity + support + vendors | Operations | Volume/vendor decisions | Not met | Complete operational decisions | TBD
REF Reference slice | Tenant/branch/catalog/API/audit/Worker/isolation | Architecture/Delivery | Prior gates | Not authorized | Start only after readiness approval | Blocked

## Volume_Assumptions
Capacity and Load-Test Assumptions
Confirmed business targets are inputs; TBD peak/size assumptions must be measured before production approval.
Metric | Normal tenant | Large owner tenant | Platform horizon | Unit | Status | Validation method
Clinic tenants |  |  | 10 | year 1 | Confirmed | Business target
Clinic tenants |  |  | 50 | year 3 | Confirmed | Business target
Branches | <10 | <10 |  | per tenant | Confirmed | Business target
Staff users | 1-20 | TBD |  | per clinic | Confirmed | Business target
Registered patients | 100000 | 2000000 |  | records | Confirmed | Migration/load dataset
Appointments/day | 100 | 2000 |  | per business day | Confirmed | Load test
Peak concurrent users | TBD | TBD |  | sessions | TBD | Pilot observation
Messages/day | TBD | TBD |  | deliveries | TBD | Workflow estimate
Documents/day | TBD | TBD |  | uploads/outputs | TBD | Pilot observation
Scheduled reports/day | TBD | TBD |  | executions | TBD | Report workshop