## Summary
BOOKDOC2026 - Requirements & Traceability
Pre-development baseline. Yellow cells are controlled planning inputs; TBD means evidence or owner confirmation is still required.
Metric | Value | Source / interpretation
Pilot jurisdiction | Delhi | Confirmed PD-006
Initial specialties | Physiotherapy; Orthopaedics | Confirmed PD-007
Clinic tenants - year 1 | 10 | Confirmed PD-013
Clinic tenants - year 3 | 50 | Confirmed PD-014
Normal tenant registered patients | 100000 | Confirmed PD-011
Typical appointments/day | 100 | Confirmed PD-012
Large-tenant appointments/day | 2000 | Confirmed PD-012
Primary legacy reports | 45 | Verified source inventory
Legacy export variants | 43 | Verified source inventory
Open requirements | 11 | Formula: requirements not Confirmed/Approved
Open decisions/risks | 6 | Formula: TBD or Proposed

## Roles_Permissions
Roles and Permission Matrix
Server authorization is the source of truth. Host visibility never grants permission.
Role | Host | Scope | Dashboard | Key permissions | Restricted actions | Approval owner | Status
Platform Operator | Control plane | All tenants - operational metadata only | Service health | Tenant applications; document types; verification monitoring | No standing clinical access | Platform owner | Confirmed
Clinic Owner | Admin + Portal | Own tenant; approved branches | Business and compliance | Users; branches; reports; configuration delegation | Cannot self-activate tenant or manage platform document types | Platform operator | Confirmed
Clinic Administrator | Admin + Portal | Own tenant/assigned branches | Configuration and operations | Users; catalogs; schedules; branch configuration if granted | Privileged grants require policy | Clinic owner | Confirmed
Receptionist | Portal | Assigned branches | Arrivals/bookings/queues | Patient register; appointment; check-in | Masked clinical and financial data | Clinic admin | Confirmed
Doctor / Orthopaedist | Portal + MAUI | Care relationship/assigned branches | Agenda and clinical work | Encounter; prescription; investigation; sign | No tenant administration | Clinic admin | Confirmed
Physiotherapist | Portal + MAUI later | Assigned patients/branches | Care plan and sessions | Assessment; care plan; session; discharge | Prescription authority not implied | Clinic admin | Confirmed
Nurse | Portal + MAUI later | Assigned branches | Queue/vitals/tasks | Vitals; tasks; permitted care notes | Signing/prescribing separately granted | Clinic admin | Confirmed
Cashier | Portal | Assigned branches | Collections and close | Invoice; receipt; close | Refund/discount approval separated | Finance owner | Confirmed
Radiology Technician | Portal | Assigned service points | Modality worklist | Arrival; scan workflow; status | Verification/release separately granted | Clinical owner | Confirmed
Lab Technician | Portal | Assigned service points | Lab worklist | Collection; result entry | Verification/release separately granted | Clinical owner | Confirmed
Patient | Patient Portal + MAUI | Self and approved representation | Own appointments/records | Book; preferences; released documents | No staff/tenant operations | Clinic policy | Confirmed
Auditor | Admin | Explicit tenant/branch period | Audit and compliance | Read audit; approved reports | No business mutation | Clinic owner | Proposed

## Workflows
Workflow and Use-Case Catalog
Stable IDs connect requirements, APIs, data and tests. Detailed exceptions remain workshop outputs.
ID | Module | Actor | Outcome | Main exception | Permission/scope | Release | Owner | Status
TEN-01A | Platform | Clinic applicant | Submit onboarding form/files | Missing/expired/rejected evidence | Own application | R0 | Platform owner | Confirmed
TEN-01B | Platform | Platform operator | Directly register clinic application | Duplicate legal entity/owner | Control plane | R0 | Platform owner | Confirmed
TEN-01C | Platform | Platform operator | Approve and provision tenant | Reject/resubmit/suspend | Platform approval | R0 | Platform owner | Confirmed
TEN-04 | Platform | Authorized branch administrator | Manage allow-listed branch override | Provider verification/version conflict | Authorized branch + configuration permission | R1 | Clinic owner | Confirmed
PAT-01 | Patient Registry | Receptionist | Register temporary/full patient | Possible duplicate | Tenant + branch | R1 | Patient owner | Proposed
SCH-02 | Scheduling | Staff/patient | Hold and book required resources | Final capacity conflict | Tenant + branch + resources | R1 | Scheduling owner | Proposed
QUE-01 | Queue | Receptionist | Check in and issue ticket | Duplicate arrival | Branch + service point | R1 | Queue owner | Proposed
PHY-01 | Clinical | Physiotherapist | Complete initial assessment | Red flag referral | Care relationship | R2 | Clinical owner | Proposed
PHY-02 | Clinical | Physiotherapist | Create goals-based care plan | Plan revision/hold | Care relationship | R2 | Clinical owner | Proposed
PHY-03 | Clinical | Physiotherapist | Document treatment session | Correction/adverse response | Assigned patient | R2 | Clinical owner | Proposed
ORT-01 | Clinical | Orthopaedist | Complete history/examination | Urgent red flag | Care relationship | R2 | Clinical owner | Proposed
ORT-02 | Clinical | Orthopaedist | Order/review imaging and plan | External result missing | Care relationship | R2 | Clinical owner | Proposed
BIL-02 | Billing | Cashier | Collect and issue receipt | Duplicate callback/split tender | Branch + billing | R3 | Finance owner | Proposed
COM-01 | Messaging | Worker | Deliver approved notification | Provider outage/dead letter | Tenant + consent | R4 | Platform owner | Proposed
REP-02 | Reporting | Admin | Schedule and distribute report | Scope revoked at execution | Admin + report + scope | R3 | Reporting owner | Proposed
PRN-02 | Printing | Portal/agent | Print receipt/slip/label | Offline/wrong branch/duplicate | Branch + printer | R5 | Operations owner | Deferred

## Requirements
Functional Requirements
Each Must requirement needs owner, acceptance examples, authorization-negative tests and tenant-isolation evidence.
ID | Module | Requirement | Priority | Permission/scope | Acceptance summary | Owner | Status | Source document
FR-TEN-001 | Platform | Reject missing, forged or unauthorized tenant scope | Must | All hosts | Cross-tenant reads/writes return authorized failure | Security owner | Confirmed | 12/16
FR-TEN-003 | Platform | Only platform operator approves and activates clinic tenant | Must | Control plane | Applicant cannot self-activate | Platform owner | Confirmed | 16
FR-TEN-005 | Platform | Use versioned dynamic document types and secured files | Must | Platform catalog | Missing/expired/replaced evidence explicit | Platform owner | Confirmed | 16
FR-TEN-007 | Platform | Clinic-submitted and operator-created applications use approval gate | Must | Control plane | No active access before approval | Platform owner | Confirmed | 16
FR-TEN-008 | Platform | Authorized branch admins self-manage allow-listed overrides | Must | Branches.Configuration.Manage + branch | Unauthorized scope/version rejected; provider-gated identity unusable | Clinic owner | Confirmed | 12/16/23
FR-PAT-001 | Patient | Masked tenant-scoped search; reviewed duplicate merge | Must | Patients.View/Merge | No auto-merge by name/mobile | Patient owner | Proposed | 16
FR-SCH-001 | Scheduling | Exactly one booking gets final capacity | Must | Appointments.Book | Concurrency test proves one winner | Scheduling owner | Proposed | 16
FR-SCH-002 | Scheduling | Reserve provider/room/modality atomically | Must | Appointments.Book | All resources reserve or none | Scheduling owner | Proposed | 16
FR-QUE-001 | Queue | Concurrency-safe queue with API recovery | Must | Queue actions | Duplicate/out-of-order SignalR converges | Queue owner | Proposed | 16
FR-ENC-001 | Clinical | Signed records immutable; corrections are amendments | Must | Encounters.Sign/Amend | Prior version/hash retained | Clinical owner | Proposed | 16
FR-PHY-001 | Clinical | Version physiotherapy measures, goals and sessions | Must | Care relationship | Reassessment does not overwrite baseline | Clinical owner | Proposed | 16/24
FR-PHY-002 | Billing/Clinical | Package consumption cannot erase clinical sessions | Must | Billing + clinical | Refund/expiry preserves clinical note | Finance/clinical | Proposed | 16/24
FR-ORT-001 | Clinical | Require site/laterality when applicable | Must | Care relationship | Missing site/side blocks signing | Clinical owner | Proposed | 16/24
FR-BIL-001 | Billing | Issued invoice retains number, price and tax snapshot | Must | Billing.Invoice | Correction uses reversal/credit | Finance owner | Proposed | 16
FR-COM-001 | Messaging | Validate template, consent and idempotency | Must | Messaging policy | Retry never duplicates business action | Platform owner | Proposed | 16
FR-REP-001 | Reporting | Require host + report permission + durable scope | Must | Report permissions | Forged branch/report rejected | Reporting owner | Proposed | 11/16
FR-PRN-001 | Printing | Browser/PDF default; agent only receipt/slip/label | Should | Printing.Submit | Wrong branch/duplicate/offline tested | Operations owner | Deferred | 11/16

## Test_Traceability
Test Traceability Matrix
IDs are planning placeholders. Test implementation remains future work.
Test ID | Requirement/workflow | Layer | Scenario | Expected evidence | Dataset | Owner | Status
T-TEN-001 | FR-TEN-001 | API integration | Forged tenant and branch | 401/403 plus no data leakage | Two tenants | Security QA | Proposed
T-TEN-002 | FR-TEN-007 | E2E | Clinic submit vs operator-created application | Both require approval before access | Synthetic applications | Platform QA | Proposed
T-TEN-003 | FR-TEN-008 | Authorization | Authorized/unauthorized branch configuration and unverified sender | Scoped change audited; unauthorized denied; unverified identity unusable | Branch users + provider event | Security QA | Proposed
T-SCH-001 | FR-SCH-001 | SQL/API concurrency | Two requests for final slot | Exactly one succeeds | Synthetic | Scheduling QA | Proposed
T-PHY-001 | FR-PHY-001 | Domain/API | Reassessment after signed baseline | New version; baseline unchanged | Anonymized examples | Clinical QA | TBD
T-ORT-001 | FR-ORT-001 | Domain/UI | Sign applicable procedure without laterality | Blocked with clear error | Synthetic | Clinical QA | TBD
T-BIL-001 | FR-BIL-001 | Integration | Attempt edit issued invoice | Rejected; reversal path available | Golden finance set | Finance QA | Proposed
T-WRK-001 | COM/REP jobs | Worker integration | Crash after claim/provider call | Lease recovery and explicit ambiguity | Synthetic provider | Platform QA | Proposed
T-REP-001 | FR-REP-001 | Authorization | Portal user requests cross-branch financial report | Denied unless all three checks pass | Two branches | Reporting QA | Proposed
T-LOAD-001 | Capacity | Performance | 10 tenants; normal and large profiles | Approved p95; no starvation | 100k + 20x datasets | Performance QA | TBD

## Risks_Decisions
Risk and Decision Register
Confirmed decisions are separated from unresolved risks. Dates use YYYY-MM-DD.
ID | Type | Topic | Decision / risk | Owner / mitigation | Status | Due / review | Source
PD-006 | Decision | Jurisdiction | Delhi first pilot | Product owner | Confirmed | 2026-08-09 | 23
PD-007 | Decision | Specialties | Physiotherapy and Orthopaedics first | Clinical owner | Confirmed | 2026-08-09 | 23/24
PD-013 | Decision | Scale | 10 tenants year 1; 50 by year 3 | Platform owner | Confirmed | 2026-08-09 | 23
PD-017 | Decision | Onboarding | Platform-only document-type management | Platform owner | Confirmed | 2026-08-09 | 23
R-001 | Risk | Compliance | Delhi establishment/professional applicability unresolved | Named Indian counsel/clinic reviewer | TBD | Before R0 approval | 17
R-002 | Risk | Capacity | Peak concurrency/messages/documents not measured | Run pilot-volume workshop and load model | TBD | Before production sizing | 17/21
R-003 | Risk | Clinical | Specialty fields/outcome tools not approved | Ten anonymized acceptance cases per specialty | TBD | Before R2 | 24
R-004 | Risk | Migration | Live DB procedures/rules not fully inventoried | Read-only schema and anonymized sample | TBD | G0 | 01/05
R-005 | Risk | Reporting | Active reports and formulas not user-validated | Classify 45 primary + 43 variants | Proposed | RP0 | 11
R-006 | Risk | Operations | Provider and printer choices unknown | Vendor/hardware readiness gate | TBD | Before affected release | 20/21